## Risk Tracking Template
Risk Register
Date of last review:
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
1 | Some questions or options might not display correctly | This can confuse users and create an unfair testing experience | Test the user interface thoroughly on different devices and screen sizes | Medium | QA Team | Include testing for both desktop and mobile browsers
2 | Poor internet connectivity could interrupt quizzes | Students might face delays or fail to submit answers | Add retry logic and allow temporary offline saving if needed | Medium | Development Team | Optimize for slower connections during testing
3 | The system may slow down or become unresponsive under heavy usage | Users could abandon the platform due to poor performance | Use scalable infrastructure and load balancing to maintain performance | High | DevOps Engineer | Monitor real-time performance and set up alerts
4 | Lack of accessibility features for users with disabilities | Could exclude some users and fail to meet accessibility standards | Design the platform to be screen-reader friendly and keyboard accessible | Low | UI/UX Team | Follow guidelines during design
5 | Errors in the quiz scoring algorithm | Users may receive incorrect results, harming trust in the system | Validate scoring logic with peer reviews and automated test cases | High | Backend Developer | Include edge cases in testing scenarios
6 | Styling conflicts could affect the user interface | Results in inconsistent layout or broken visuals | Use scoped styles and follow a consistent design system | Low | UI/UX Team | Regular visual checks and responsive testing
7 | Invalid input during quiz creation can lead to broken quizzes | Affects both quiz quality and user experience | Add form validations on both client and server side | Medium | Full-stack Developer | Restrict inputs to expected formats and values
8 | The platform may not work consistently across all devices | Users on mobile or tablet may face issues | Ensure responsive design and cross-browser compatibility | Medium | UI/UX Developer | Test on multiple screen sizes and browsers
9 | Quiz data could be lost if the system fails unexpectedly | Permanent loss of important data and user responses | Implement automated backups and regular recovery tests | High | Project Manager | Store backups securely with redundancy
10
11
12
13
14
15
16
17
18
19